## FDAS 100% COMPLETION
FDAS WIRING ACCOMPLISHMENT% PER FLOOR |  |  |  | FDAS FIXTURES ACCOMPLISHMENTS |  |  | FDAS COMMISSION AND TESTING PER FLOOR |  |  | FDAS AS BUILT PLAN
FLOOR | MATERIAL | UNIT | QTY | FLOOR | UNIT | QTY | FLOOR | UNIT | QTY | FLOOR | UNIT | QTY
MACHINE ROOM | 16 GAUGE UTP CABLE | l.m. | 0 | MACHINE ROOM | PCS | 0 | MACHINE ROOM | PCS | 0 | MACHINE ROOM | ASSY | 1
ROOF DECK | 16 GAUGE UTP CABLE | l.m. | 0 | ROOF DECK | PCS | 0 | ROOF DECK | PCS | 0 | ROOF DECK | ASSY | 1
8TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 480 | 8th | PCS | 83 | 8th | PCS | 83 | 8TH FLOOR | ASSY | 1
7TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 480 | 7th | PCS | 83 | 7th | PCS | 83 | 7TH FLOOR | ASSY | 1
6TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 480 | 6th | PCS | 83 | 6th | PCS | 83 | 6TH FLOOR | ASSY | 1
5TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 560 | 5th | PCS | 6 | 5th | PCS | 6 | 5TH FLOOR | ASSY | 1
4TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 560 | 4th | PCS | 104 | 4th | PCS | 104 | 4TH FLOOR | ASSY | 1
3RD FLOOR | 16 GAUGE UTP CABLE | l.m. | 560 | 3rd | PCS | 104 | 3rd | PCS | 104 | 3RD FLOOR | ASSY | 1
2ND FLOOR | 16 GAUGE UTP CABLE | l.m. | 350 | 2nd | PCS | 71 | 2nd | PCS | 71 | 2ND FLOOR | ASSY | 1
GROUND FLOOR | 16 GAUGE UTP CABLE | l.m. | 280 | 1st | PCS | 41 | 1st | PCS | 41 | GROUND FLOOR | ASSY | 1
B1 | 16 GAUGE UTP CABLE | l.m. | 220 | B1 | PCS | 24 | B1 | PCS | 24 | B1 | ASSY | 1
B2 | 16 GAUGE UTP CABLE | l.m. | 220 | B2 | PCS | 15 | B2 | PCS | 15 | B2 | ASSY | 1
B3 | 16 GAUGE UTP CABLE | l.m. | 220 | B3 | PCS | 16 | B3 | PCS | 16 | B3 | ASSY | 1
B4 | 16 GAUGE UTP CABLE | l.m. | 220 | B4 | PCS | 16 | B4 | PCS | 16 | B4 | ASSY | 1
B5 | 16 GAUGE UTP CABLE | l.m. | 220 | B5 | PCS | 12 | B5 | PCS | 12 | B5 | ASSY | 1
B6 | 16 GAUGE UTP CABLE | l.m. | 220 | B6 | PCS | 12 | B6 | PCS | 12 | B6 | ASSY | 1
TOTAL | 16 GAUGE UTP CABLE | l.m. | 5070 | TOTAL | PCS | 670 | TOTAL | PCS | 670 | TOTAL | ASSY | 16
ACCOMPLISHMENT % |  | 100% |  | ACCOMPLISHMENT % |  | 100% | ACCOMPLISHMENT % |  | 100% | ACCOMPLISHMENT % |  | 100%
TOTAL % |  | 50% |  | TOTAL % |  | 30% | TOTAL % |  | 10% | TOTAL % |  | 10%

## FDAS BILLING NO.2
2022-11-15
Project: | CITY HUB CONDOTEL |  |  |  |  | Subject: | FDAS
Location: | #92 Upper General Luna Corner Leonard Wood Road, Baguio City |  |  |  |  | Sub Contractor: | MR. MARCELINO DISU
FDAS WIRING ACCOMPLISHMENT% PER FLOOR |  |  |  | TOTAL FIXTURES |  |  | FDAS COMMISSION AND TESTING PER FLOOR |  |  | FDAS AS BUILT PLANS
FLOOR | MATERIAL | UNIT | QTY | FLOOR | UNIT | QTY | FLOOR | UNIT | QTY | FLOOR | UNIT | QTY
MACHINE ROOM | 16 GAUGE UTP CABLE | l.m. |  | MACHINE ROOM | PCS | 0 | MACHINE ROOM | PCS | 0 | MACHINE ROOM | ASSY | 0
ROOF DECK | 16 GAUGE UTP CABLE | l.m. | 0 | ROOF DECK | PCS | 0 | ROOF DECK | PCS | 0 | ROOF DECK | ASSY | 0
8TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 480 | 8th | PCS | 0 | 8th | PCS | 0 | 8TH FLOOR | ASSY | 0
7TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 480 | 7th | PCS | 0 | 7th | PCS | 0 | 7TH FLOOR | ASSY | 0
6TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 480 | 6th | PCS | 0 | 6th | PCS | 0 | 6TH FLOOR | ASSY | 0
5TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 528 | 5th | PCS | 0 | 5th | PCS | 0 | 5TH FLOOR | ASSY | 0
4TH FLOOR | 16 GAUGE UTP CABLE | l.m. | 560 | 4th | PCS | 0 | 4th | PCS | 0 | 4TH FLOOR | ASSY | 0
3RD FLOOR | 16 GAUGE UTP CABLE | l.m. | 560 | 3rd | PCS | 0 | 3rd | PCS | 0 | 3RD FLOOR | ASSY | 0
2ND FLOOR | 16 GAUGE UTP CABLE | l.m. | 341 | 2nd | PCS | 0 | 2nd | PCS | 0 | 2ND FLOOR | ASSY | 0
GROUND FLOOR | 16 GAUGE UTP CABLE | l.m. | 257 | 1st | PCS | 0 | 1st | PCS | 0 | GROUND FLOOR | ASSY | 0
B1 | 16 GAUGE UTP CABLE | l.m. | 67 | B1 | PCS | 0 | B1 | PCS | 0 | B1 | ASSY | 0
B2 | 16 GAUGE UTP CABLE | l.m. | 0 | B2 | PCS | 0 | B2 | PCS | 0 | B2 | ASSY | 0
B3 | 16 GAUGE UTP CABLE | l.m. | 0 | B3 | PCS | 0 | B3 | PCS | 0 | B3 | ASSY | 0
B4 | 16 GAUGE UTP CABLE | l.m. | 0 | B4 | PCS | 0 | B4 | PCS | 0 | B4 | ASSY | 0
B5 | 16 GAUGE UTP CABLE | l.m. | 0 | B5 | PCS | 0 | B5 | PCS | 0 | B5 | ASSY | 0
B6 | 16 GAUGE UTP CABLE | l.m. | 0 | B6 | PCS | 0 | B6 | PCS | 0 | B6 | ASSY | 0
TOTAL | 16 GAUGE UTP CABLE | l.m. | 3753 | TOTAL | PCS | 0 | TOTAL | PCS | 0 | TOTAL | ASSY | 0
WIRING ACCOMPLISHMENT % |  | 74.02% |  | FIXTURE INSTALL ACCOMPLISHMENT % |  | 0% | TESTING ACCOMPLISHMENT % |  | 0% | TESTING ACCOMPLISHMENT % |  | 0%
TO DATE GROSS % ACCOMPLISHMENT |  | 37.01% |  | TO DATE GROSS % ACCOMPLISHMENT |  | 0% | TO DATE GROSS % ACCOMPLISHMENT |  | 0% | TO DATE GROSS % ACCOMPLISHMENT |  | 0%
THIS DATE'S GROSS % ACCOMPLISHMENT |  | 20.35% |  | THIS DATE'S GROSS % ACCOMPLISHMENT |  | 0% | THIS DATE'S GROSS % ACCOMPLISHMENT |  | 0% | THIS DATE'S GROSS % ACCOMPLISHMENT |  | 0%
PREVIOUS GROSS ACCOMPLISHMENT % |  | 16.67% |  | PREVIOUS GROSS ACCOMPLISHMENT % |  | 0% | PREVIOUS GROSS ACCOMPLISHMENT % |  | 0% | PREVIOUS GROSS ACCOMPLISHMENT % |  | 0%
TOTAL COST OF CONTRACT |  | 700000 |  | TOTAL GROSS ACCOMPLISHMENT |  | 259082.8402 | CASH ADVANCES: |  |  | DEDUCTED CASH ADVANCES AND MOB. FEES
THIS DATE'S ACCOMPLISHMENT |  | 142416.1736 |  | PREVIOUS BILLING ACCOMPLISHMENT |  | 116666.6667 | MOBILIZATION FEE | 70000 |  | MOB. FEES: | 20000
LESS 10% RETENTION |  | 14241.6174 |  | TOTAL CA AND MOB. FEE |  | 130000 | CA OCT. 8, 2021 | 30000 |  | CA OCT.8,2021 | 30000
LESS MOB. FEE (RECOUPMENT) |  | 50000 |  | TOTAL DEDUCTIONS THIS DATE |  | 50000 | CA OCT.23 ,2021 | 20000 |  | CA OCT.23,2021 | 20000
LESS CASH ADVANCE (OCTOBER 23,2021) |  | 0 |  | PREVIOUS DATE DEDUCTIONS |  | 80000 | CA AUG.3,2021 | 10000 |  | CA AUG 3.2021 | 10000
NET ACCOMPLISHMENT |  | 78174.5562 |  | TOTAL DEDUCTIONS TO DATE |  | 130000
PREPARED BY: |  |  |  |  | APPROVED BY:
PATRICK GO |  | MARCELINO DISU |  |  | SHIELAMAR REYES |  | MARCIANO GARCIA |  | MARK GARCIA |  | MARTELL GARCIA
ELECTRICAL IN CHARGE |  | SUBCON PIC |  |  | HEAD OF DESIGN TEAM |  | CEO OF MBC |  | HEAD OF PROCUREMENT |  | PRESIDENT OF MBC

## MATERIAL SHEET
Column1 | B6 | B5 | B4 | B3 | B2 | B1 | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | TOTAL
ADDRESSABLE SMOKE DETECTOR | 2 | 2 | 7 | 7 | 4 | 12 | 32 | 56 | 57 | 57 | 6 | 45 | 45 | 45 | 375
MONITOR MODULE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 24
SUPERVISORY SWITCH | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12
FLOW SWITCH | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12
FIREMAN'S TELEPHONE OUTLET | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12
ANNUNCIATOR | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 12
FIRE ALARM SOUNDER WITH STROBE LIGHT | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 4 | 4 | 0 | 3 | 3 | 3 | 27
ADRESSABLE MANUAL PULL STATION | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 4 | 4 | 0 | 3 | 3 | 3 | 27
CONTROL MODULE | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 4 | 4 | 0 | 3 | 3 | 3 | 27
HEAT DETECTOR | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 29 | 29 | 0 | 23 | 23 | 23 | 130
TOTAL FIXTURES | 12 | 12 | 16 | 16 | 15 | 24 | 41 | 71 | 104 | 104 | 6 | 83 | 83 | 83 | 658

## DOCUMENT CONTROL
CONTROL DOCUMENT FOR FDAS BILLING PROCEDURE | PROJECT : | CITYHUB
| LOCATION : | 92 UPPER GENERAL LUNA, BAGUIO CITY
| ___ Structural |  | ___ Sanitary/ Plumbing | Date: |  | Control No.
| ___ Architectural |  | ___ FDAS/BAS | 2022-11-14
| ___ EE/ECE |  | ___ FIRE PRO
| ___ Mechanical |  | ___ Others
THIS DOCUMENT CERTIFIES WHAT FOLLOWS . PROGRESS BILLING PROCESS FOR FDAS WORKS SHALL BE GRADED AS 50 % FOR WIRING WORKS 30% FOR FIXTURE INSTALLATION, 10% FOR COMMISSION AND TESTING AND 10% FOR AS BUILT PLANS. ASSUMING THE VARIABLE W AS WIRING ACCOMPLISHMENTS, X AS FIXTURE INSTALLATION ACCOMPLISHMENTS, Y AS COMMISSION AND TESTING ACCOMPLISHMENTS AND Z AS AS BUILT PLAN ACCOMPLISHMENTS , THE FORMULA FOR COMPUTING BILL TO BE RELEASED SHALL BE: 0.5*W + 0.3*X + 0.1*Y + 0.1*Z
PREPARED BY: | WITNESSED BY: |  |  |  | APPROVED BY:
PATRICK GO | MARCELINO DISU |  |  |  | MARCIANO GARCIA
In-House Electrical Engineer | Subcon PIC |  |  |  | CEO of MBC
DISTRIBUTION : |  |  |  |  | ___ MBC Document Control